## Slide 1
Technology Transfer Accelerator Turkey
(TTA Turkey)
Nur Özdemir
EIF

## Slide 2
TTA Turkey’s main purpose is to:
  Establish 2 (two) independently managed Technology Transfer Accelerator Funds that invest in commercialisation of technology intensive research coming out of universities and research centres
  Increase the R&D commercialisation capacities of TTOs and TÜBİTAK so that they can play a successful interface role between the industry and the university
TTA Turkey Project Structure and Main Objectives
IPA Resources
EIF as Advisor & Project Manager
IPA Commitment to
TTA Turkey Fund
Advisory Services and Networking
(Technical Assistance)
TTOs
TÜBİTAK
Visibility
Impact Evaluation
proceeds
  Put in operation on 25 July 2014
  Original size of operation: EUR 30.5m
  Budget increase of EUR 18.3m signed on 22 December 2014

## Slide 3
TTA Turkey Progress on Implementation
  Information Session: 5 August 2014
Launch Event: 10 September 2014
Call for Expression of Interest IPA-001/2
28 July 2014 – 11 September 2014
First fund manager approved by EIF BoD on 17 November 2014 (“TTA Turkey Fund I”)
  IPA commitment of EUR 26.3m
  Minimum of EUR 2.8m third party capital
First closing reached on 1 April 2015
Call for Expression of Interest IPA-001/2.1
23 December 2014 – 4 February 2015
Second fund manager approved by EIF BoD on 20 April 2015 (“TTA Turkey Fund II”)
  IPA commitment of EUR 18.3m
  Minimum of EUR 3.2m third party capital
First closing reached on 22 July 2015

## Slide 4
TTA Turkey Advisory Services Component
  Selecting tenderers following a public procurement procedure (OJEU)
  Prior Information Notice published on 28 May 2015
  Procurement Notice published on 30 June 2015
  Shortlist Notice published on 21 August 2015
  Expected signature date with the selected consultant(s) in November 2015
  EUR 1.35m budget
  The purposes of this component are to:
  a. improve the capacity of technology transfer offices in Turkey
  b. advance TÜBİTAK’s capacity in the field of commercialisation of R&D,
  c. increase the ability of TTA Turkey Funds to source deals
  by taking into account the technology transfer landscape of Turkey, its unique players and dynamics.

## Slide 5: Thank You
EIF
37B, avenue J. F. Kennedy
L-2968 Luxembourg
T :(+352) 2485-1
F :(+352) 2485-81200
www.eif.org
tta_turkey@eif.org
eifturkeyteam@eif.org
Notes: 5